## Slide 1
SALES TRAINING DECK
API Integration Process
The 9-Step End-to-End Process Every Sales Rep Should Know
CASE STUDY
Linkstay (China) · Jun 2025 – May 2026 · approx. 11 months
Prepared by Global Sales & Marketing | May 2026

## Slide 2
Learning Objectives & Case Study Overview
What you will take away from this training
OMH Global Sales Training | API Integration Process
2 / 17
01
Understand the Full Process Flow
9 steps from initial contact to Go-Live, with Sales' role and responsibilities at each stage
02
Master Standard Terms & Limits
Acceptable concession ranges for Deposit, Credit Ratio, Settlement, Currency, and more
03
Handle Key Negotiation Points
The 4 issues clients repeatedly raise during contract review, and how to respond
CASE STUDY
Linkstay
China · B2B Hotel Distribution
Client Daily Order Volume
1,500 – 2,000 orders
Channels
Ctrip, Fliggy, Meituan + 400K+ agents
Contract Type
Supplier (B2B inventory supply)
Timeline
Initial contact → Go-Live: approx. 11 months

## Slide 3
The End-to-End 9-Step Process
From initial contact to Go-Live
OMH Global Sales Training | API Integration Process
3 / 17
01
Client Meeting & Lead Generation
Account setup, top-selling list, meeting
02
NDA Dispatch & Fit Assessment
NDA for confidentiality, model & channel check
03
Commercial Terms (Settlement)
Deposit·Currency·Settlement → CEO approval
04
OMH NICE Screening & Contract·SLA
AI screening passed, then clause review & SLA split
05
Contract & DEV Key Delivery
API SPEC · DEV environment · DEV Credential
06
Development & Staging Test
Certification on unified test scenario
07
Test Completion & Deposit
Cert result verified + payment received
08
Live Key Issuance & Live Test
Dev team → Sales → Client, Live Test
09
Go-Live / Live Completion
Schedule notice, monitoring, official launch
★ Gold-marked steps (3, 7, 9) are the key decision/gate points where Sales must focus most

## Slide 4
PHASE 1
Lead Generation & Initial Contact
From interest → account setup → follow-up
OMH Global Sales Training | API Integration Process
4 / 17
Sales Actions
1
Issue ohmyhotel.biz account (with temporary password)
2
Share top-selling hotel lists by country (KR/JP/VN)
3
Explain prepayment policy (credit card or bank transfer)
4
Regular follow-up if client is unresponsive (every 3–6 weeks)
5
Clarify client's business counterparts (R&D, Procurement)
Linkstay Case
2025.06.26 Jensen issued account + sent top-selling list
2025.06.27 Jason (Linkstay) expressed pricing interest + requested contract
2025.07.30 Grace's first follow-up (no response)
2025.09.12 Second follow-up → partnership interest reconfirmed
KEY LESSON
Never give up on a silent lead
Linkstay went silent for about 3 months after first contact (Jun → Sep) before re-engaging. Consistent follow-up is what ultimately closes the deal.
GATE ▸ Move to Phase 2 once client confirms intent to partner + timeline is shared

## Slide 5
PHASE 2
NDA Dispatch & Business Fit Assessment
Secure confidentiality, then map client model & channels
OMH Global Sales Training | API Integration Process
5 / 17
STEP 1. Send NDA (for confidentiality)
Send OMH NDA template right after the client meeting (Sales drives)
Client signs & returns → send our countersigned copy
Share pricing, inventory and API materials only after the NDA
STEP 2. Fit Questions (5 Must-Asks)
Q1.
Main sales channels (B2B / B2C / WeChat, etc.)
Q2.
B2B vs B2C revenue mix
Q3.
Average daily order volume (expected volume)
Q4.
Inventory supply method (API / Static / Cross-Selling)
Q5.
Payment & settlement currencies (USD / JPY / CNY)
Linkstay's Answers (Actual)
Sales Channels
Ctrip · Fliggy · Meituan (B2B) + 400K+ WeChat agents (B2C)
B2B vs B2C
Mostly B2B (overseas 3rd-party suppliers limited to private channels like WeChat)
Daily Order Volume
1,500 – 2,000 orders (overseas transactions)
Sales Method
Auto-confirmation via API / self-managed settlement
Payment Currency
USD (as negotiated)

## Slide 6
PHASE 3
Commercial Terms Negotiation (Settlement)
Agree Deposit · Currency · Settlement → CEO approval
OMH Global Sales Training | API Integration Process
6 / 17
Deposit
OMH Standard
USD 30,000
Negotiated
USD 10,000
(Linkstay)
Negotiable by tier & volume
Credit Ratio
OMH Standard
1:1
Negotiated
Kept at 1:1
Hold the line — no concessions
Settlement
OMH Standard
Bi-Weekly
Negotiated
Bi-Weekly
(based on check-out)
Cycle kept at standard
Currency
OMH Standard
USD
Negotiated
USD
(JPY proposal declined)
Stick to USD as base currency
★ All four terms need CEO approval before they are final — never commit to the client beforehand. In-person meetings accelerate negotiation (Linkstay, ITB Singapore Oct 15).

## Slide 7
PHASE 4
OMH NICE Screening & Contract · SLA
Pass AI screening → clause review → split SLA → signature
OMH Global Sales Training | API Integration Process
7 / 17
Progress timeline (Linkstay actual)
10/17
OMH sends draft contract (after NICE screening)
11/13
Client returned comments (incl. proposal to add SLA)
11/26
OMH review reply + highlighted comments
12/05
Discussed referencing SLA in contract clauses III.3, IV.3
12/09
Decided to split SLA into separate doc + sent revised contract
01/09
Both parties signed contract + SLA
Top 4 Recurring Client Issues
1
Handling when booked rate can't be honored at check-in
→ Codify the solution. Define specific handling criteria in the SLA
2
Scope of "Party B rights & obligations"
→ Clarify whether limited to API distribution or including websites
3
Billing dispute resolution deadline
→ Clients say 5 working days is too short. Review together with penalty clause
4
1% Daily Payment Penalty
→ Negotiate a proviso on whether it applies during disputes

## Slide 8
PHASE 5
API SPEC · DEV Environment · DEV Key
Sales request → Dev team issues → Sales → Client
OMH Global Sales Training | API Integration Process
8 / 17
Sales Action Checklist
Store signed PDF on both sides (OMH HQ / Client)
1. Request DEV Credential from dev team (Sales)
2. Share API SPEC Site (developer.ohmyhotel.com)
3. Deliver DEV URL + DEV Key (Token · Secret)
4. Collect client IT contacts + access IP addresses
5. Connect OMH tech team (@API SUPPORT)
6. Create MS Teams group → IT-to-IT direct comms
Client Delivery Package
Signed Contract
Signed PDF, both parties
API SPEC Site
developer.ohmyhotel.com
DEV Environment
dev-api-ota-v2.ohmyhotel.com
DEV Credential Key
API Token + Secret (issued by dev team)
Teams Channel
Client IT ↔ OMH Dev Team

## Slide 9
PHASE 6
Test Scenario & Staging Test
Distribute scenario → staging test → submit Cert
OMH Global Sales Training | API Integration Process
9 / 17
Provided by OMH
API Client Certification V2.1
Normal / 3rd include / Package rate → unify into one
Hotel Static Information
Hotel master + room info (weekly update)
Staging environment + test hotel code
Common scenarios on Hotel Code 764481
API debugging support
Real-time IT-to-IT response via Teams
Client Deliverables
API Test Result + Log
All 6 API request/response sets (Availability → Cancel)
Completed Certification Form
Client Detail · Technical Support · access IPs
Voucher screen capture
Must show Payable by + Emergency contact
Prior Acknowledgement sign-off
6 items incl. static storage, mapping, MSP
KEY ▸ Communication rule — Client IT ↔ OMH Dev Team direct. Sales manages schedule and escalation (PM mode)

## Slide 10
PHASE 7
Test Completion & Deposit
Two prerequisites for live key issuance
OMH Global Sales Training | API Integration Process
10 / 17
Test completion → payment process
1
Receive Cert document + logs
Client IT submits directly to OMH dev team
2
Internal verification by dev team
Check 6 API responses · voucher requirements
3
Test completion (Pass) decision
Re-test requested for any gap
4
Deposit payment request
Designated USD account · bank fee borne by Party B
5
Payment confirmed → live key approved
Cert Pass AND deposit — both conditions required
Linkstay Payment Example
USD 10,000
Deposit · Credit Ratio 1:1
Payment Currency
USD
Bank Fee
Paid by Linkstay
Transfer Date
2026.04.30
Proof Provided
Wire transfer receipt PDF
Live Credentials Issued
After OMH review

## Slide 11
PHASE 8
Certification (Live Key) & Live Test
Dev team → Sales → Client delivery + live booking check
OMH Global Sales Training | API Integration Process
11 / 17
Live key issuance procedure
1
Live key issued (dev team)
PROD credentials created after Cert Pass + payment
2
Delivered via Sales
Dev team → Sales → Client (log the handover)
3
Apply to PROD + live test booking
At least one booking + booking number returned
4
OMH confirms booking → Go-Live notice
Verify in ELLIS, then announce launch D-Day
Channel Information (Both Sides)
Channel BD
New partnerships & expansion
CS
Customer support, refunds, VOC
Operation
Booking processing & inventory
Finance
Settlement, invoices, tax
IT
API & system incident response
VN OP Hours (Reference)
Weekdays 06:00–17:15 (Office) / 17:15–22:30 (Hotline)
Weekends 08:00–20:00 (Hotline)

## Slide 12
PHASE 9
Go-Live / Live Completion
Official launch + early monitoring + sell-through
OMH Global Sales Training | API Integration Process
12 / 17
Pre-Launch
D-7 ~ D-1
Officially confirm Go-Live date with both sides
Assign IT monitoring shifts on both sides
Pre-brief OMH OP/CS teams
Final check of initial inventory & rates
Launch Day
D-Day
Activate live channel (toggle on client side)
OMH dev team on standby (instant Teams response)
OMH IT on standby (instant Teams response)
Sales is the communication hub for both sides
Post-Launch
D+1 ~ D+30
Share weekly booking/revenue data
Monitor error & cancellation rates
Recommend strengthening top-selling hotels
Enter monthly settlement cycle
Linkstay actual: Cert passed (Apr 29) → deposit (Apr 30) → live key issued → Live Test (May 7) → live completion (May) — about 2 weeks

## Slide 13
OMH Standard Commercial Terms
The baselines you must know before negotiating
OMH Global Sales Training | API Integration Process
13 / 17
Term
Standard
Negotiable Range
Sales Authority
Deposit
USD 30,000
USD 10,000 (Tier 1 clients) – Bank Guarantee
Director approval
Credit Ratio
1:1
Non-negotiable (principle)
No concessions
Currency
USD
Stick to USD (decline JPY/KRW/CNY requests)
Consult Director in advance
Settlement
Bi-Weekly
Bi-Weekly (cycle non-negotiable)
No concessions
Settlement Basis
Based on check-out
Keep check-out basis
No concessions
Bank Fee
Paid by Party B (client)
No concessions
No concessions
Payment Penalty
1% / Day
Proviso possible: waived during disputes
Consult Director
Billing Dispute
5 Working Days
Negotiable up to 10 working days
Consult Manager
* Sales authority is a guideline; final approval always follows OMH HQ procedures.

## Slide 14
5-Step API Integration Process
SPEC·DEV Key → Staging Test → Test Complete → Live Key → Live
OMH Global Sales Training | API Integration Process
14 / 17
STEP 1
SPEC + DEV env
+ DEV Key
Dev → Sales → Client
STEP 2
Unified scenario
staging test
Client IT ↔ OMH Dev
STEP 3
Test completion
(Result + Log)
Client → OMH Dev Team
STEP 4
Certification
(Live Key) provided
Dev → Sales → Client
STEP 5
Live completion
(Go-Live)
Joint monitoring by both
Points Sales must never miss
1. Test scenarios are split into 3 (Normal / 3rd include / Package rate) — unifying them is the improvement task
2. Live key is issued only after BOTH Cert Pass AND deposit payment
3. Technical comms run developer-to-developer; Sales owns schedule and escalation

## Slide 15
4 Recurring Contract Negotiation Issues
Clauses clients frequently challenge + how to respond
OMH Global Sales Training | API Integration Process
15 / 17
Q1
Who is responsible if check-in fails at the booked rate?
▸ Codify specific handling procedures in the SLA — define per scenario: rebooking, refund, price-difference compensation. The contract body only references 'per the SLA'.
Q2
Do Party B's rights & obligations apply only to the API, or also to websites?
▸ Can be limited to API distribution as the client requests. But explicitly state our websites are excluded (applied in the Linkstay case).
Q3
5 working days is not enough to resolve billing disputes
▸ Negotiate toward a proviso waiving the 1% penalty while a dispute is formally raised. Extension possible up to 10 working days.
Q4
The 1% daily payment penalty is excessive
▸ Negotiable: dispute-period waiver proviso + cap clause (e.g., 30% cumulative). No concession on the base rate.

## Slide 16
Sales Checklist
'Done' criteria checklist by phase
OMH Global Sales Training | API Integration Process
16 / 17
P1 — Client Meeting
Account issued + temp password sent
Top-selling list sent
Follow-up scheduled after meeting
P2 — NDA Dispatch
Confidentiality NDA sent and returned
Secure answers to 5 fit questions
P3 — Commercial Terms
Deposit agreed + CEO approval
Currency · Settlement fixed
P4 — NICE & Contract
OMH NICE AI screening passed
Clause review + SLA as separate document
Handle 4 recurring issues
P5 — SPEC · DEV Key
Request DEV Key from dev team
Deliver SPEC Site · DEV URL · DEV Key
Set up Teams channel (IT ↔ IT)
P6 — Staging Test
Share Cert document + static info
Collect client IT contacts · access IPs
Monitor test progress
P7 — Test Complete / Deposit
Dev team verifies Result + Log
Confirm test Pass decision
Deposit received + receipt on file
P8·9 — Live Key / Go-Live
Deliver live key + live test booking
Exchange channel info both ways
Go-Live D-3 advance notice

## Slide 17
KEY TAKEAWAYS
5 things to remember
01
Sales = PM Mode
Sales is the project manager across all 9 phases. In the technical phases, however, Client IT and the OMH dev team communicate directly, while Sales owns schedule and escalation.
02
Standard is USD 30K; Floor is USD 10K
Deposit can be lowered to USD 10K, but only for Tier 1 clients. The 1:1 Credit Ratio and the bi-weekly settlement cycle are non-negotiable under any circumstances.
03
Unify test scenarios into one document
Currently split into Normal / 3rd include / Package rate. A single document with common TEST 1-4 plus one optional case is feasible.
04
AND condition — Cert Pass + Deposit
The live key is issued only when both are met, and must follow the Dev team → Sales → Client route.
05
Never Give Up on Follow-up
Linkstay re-engaged after about 3 months of silence following first contact. Consistent follow-up is what ultimately makes the deal.
OMH Global Sales & Marketing | API Integration Training | May 2026